STATE OF WASHINGTON

OFFICE OF THE SECRETARY OF STATE

OLYMPIA, WASHINGTON

REQUEST FOR PROPOSALS

RFP NO. 09-02

PROJECT TITLE:  Scanning and Metadata – National Digital Newspaper Program Grant Project

PROPOSAL DUE DATE:  October 15, 2008

EXPECTED TIME PERIOD FOR CONTRACT:  November 17, 2008 – June 30, 2010

CONSULTANT ELIGIBILITY:  This procurement is open to those consultants that satisfy the minimum qualifications stated herein and that are available for work in Washington State.

CONTENTS OF THE REQUEST FOR PROPOSALS

1.	Introduction

2.	General Information for Consultants

3.	Proposal Contents

4.	Evaluation and Award

5.	Exhibits

A.	Certifications and Assurances

B.	Sample Purchased Service Contract and General Terms and Conditions

C.  	Certification of Debarment and Suspension

D.  	Technical Guidelines

TABLE OF CONTENTS

1.	Introduction	1

1.1	Purpose and Background	1

1.2	Deliverables	1

1.3	Minimum Qualifications	3

1.4	Funding	3

1.5	Period of Performance	4

1.6	Definitions	4

2.	General Information for Consultants	4

2.1	RFP Coordinator	4

2.2	Estimated Schedule of Procurement Activities	5

2.3	Submission of Proposals	5

2.4	Proprietary Information/Public Disclosure	5

2.5	Revisions to the RFP	6

2.6	Minority & Women-Owned Business Participation	6

2.7 	Acceptance Period	6

2.8	Responsiveness	6

2.9	Most Favorable Terms	7

2.10	Contract and General Terms & Conditions	7

2.11	Costs to Propose	7

2.12	No Obligation to Contract	7

2.13	Rejection of Proposals	7

2.14	Commitment of Funds	7

2.15	Electronic Payment	8

2.16	Insurance Coverage	8

2.17   Workers Compensation Coverage…………………………………………………………………..8

.

3.	Proposal Contents	8

3.1	Letter of Submittal	8

3.2	Management Proposal	9

3.3	Cost Proposal	10

3.4     References	11

4.	Evaluation and Contract Award	11

4.1	Evaluation Procedure	11

4.2	Evaluation Weighting and Scoring	11

4.3	Notification to Proposers	12

4.4	Debriefing of Unsuccessful Proposers	12

4.5	Protest Procedure	12

5.	RFP Exhibits……..	14

Exhibit A	Certifications and Assurances

Exhibit B	Sample Purchased Service Contract including General Terms and Conditions

Exhibit C   Certificate of Disbarment and Suspension

Exhibit D   The National Digital Newspaper Program (NDNP) Technical Guidelines

1.	INTRODUCTION

1.1		PURPOSE AND BACKGROUND

The Washington State Office of the Secretary of State, Washington State Library Division, hereinafter called "AGENCY”, is initiating this Request for Proposals (RFP) to solicit proposals from firms, hereinafter called “CONSULTANTS”, interested in participating on a project to convert newspapers on microfilm to digital images and provide specific testing, metadata and optical character recognition (OCR) services according to National Digital Newspaper Program (NDNP) standards and specifications.

The Washington State Library

The State Library has served both the territory and State of Washington since 1853.  It is a government library that serves as the official depository of all state agency publications and as the regional repository for federal publications for Washington and Alaska.  The Library has also played an important part in preserving the history of Washington over the years with strong collections in Pacific Northwest history and culture, and an extensive collection of Washington newspapers on microfilm.  For the last several years the Library has conducted a small internal newspaper digitization project that can be viewed at http://www.secstate.wa.gov/history/newspapers.aspx.

National Digital Newspaper Program (NDNP) Project

The National Endowment for the Humanities (NEH) in conjunction with the Library of Congress (LOC) has selected the Washington State Library and its partners to participate in NDNP by awarding them a grant to digitize a collection of Washington’s newspapers.  The State Library is the lead institution in the state for coordinating Washington’s NDNP project.  This includes working with other large institutions to meet the requirements of the granting bodies and producing 100,000 images of Washington newspapers in a 2-year period according to NDNP specifications.  For this project the partner institutions are the University of Washington Library (UW), Washington State University Library (WSU) and Seattle Public Library (SPL).

1.2      DELIVERABLES

The following deliverables pertain to the period of performance of the purchased service contract resulting from this RFP from the date of execution.  All deliverables must have prior approval of the AGENCY contact Marlys Rudeen.

Consultant shall meet the following deliverables:

SCHEDULE

- Project deadline: Sample reel of images and metadata must be submitted to LOC by January 31, 2009.

- In order to meet this deadline - Library must receive sample files for review by December 15, 2008

- Project deadline: 25% of images and metadata must be submitted to LOC by July 31, 2009.

- In order to meet this deadline - Library should receive 50% of these images and files by April 30, 2009; the remainder should be received by June 15, 2009.

- Project deadline: The rest of the images and metadata must be submitted to LOC by June 30, 2010.

- In order to meet this deadline - The Library and vendor will decide on a delivery schedule for the second year’s production.

TECHNICAL SPECIFICATIONS

All guidelines and specifications for this project can be found at: http://www.neh.gov/grants/guidelines/ndnp.html

The technical specifications that must be met by any vendor for formats, metadata and XML templates can be found in the document and appendices titled, “The National Digital Newspaper Program (NDNP) Technical Guidelines for Applicants 2008-2010” at:

http://www.loc.gov/ndnp/pdf/NDNP_200810TechNotes.pdf  A copy of this document is attached to this RFP as “Technical Guidelines.”  The following list of deliverables is a summary and is not intended to replace or override the specifications in the above documents.

- Scanning of newspapers on microfilm in required formats:

- 8-bit Grayscale, uncompressed TIFF 6.0 image format, 300-400 dpi resolution (Technical Guidelines: Appendix B – File Format Profiles)

- Compressed JPEG2000 image (Technical Guidelines: Appendix B – File Format Profiles)

- File with optical character recognition (OCR) text and associated bounding boxes for words, 1 file per page image (Technical Guidelines: Appendix B – File Format Profiles)

- PDF image with hidden text. (Technical Guidelines: Appendix B – File Format Profiles)

- The grant requires structural metadata to relate pages to title, date, and edition; to sequence pages within issue or section; and to identify image and OCR files.  (Technical Guidelines: Appendix A – Digital Asset Metadata Elements & Appendix C – XML Metadata Templates)

- The Library will supply title, issue and page level metadata in a format agreed upon with the vendor.

- Vendor will create OCR and bounding box coordinates and integrate with the Library-supplied metadata to derive metadata files according to the NDNP metadata requirements.

- All digital assets will be delivered in a METS (Metadata Encoded Transmission Schema) object structure according to an XML batch template structure.

- Technical metadata to support the functions of a trusted repository (Technical Guidelines: Appendix A – Digital Asset Metadata Elements, Appendix B – File Format Profiles, & Appendix C – XML Metadata Templates)

Scanning Details

- Scan from clean, 2nd generation duplicate silver negative microfilm

- Capture specs: 8-bit grayscale, at the maximum resolution possible, between 300-400 dpi relative to the physical dimensions of the original newspaper, rather than the microfilm.  For the scanner operator to achieve this, the microfilm reduction ratio must be known or derived by other means.

- A standards-based target film strip should be scanned at the start of each session: to monitor scanning equipment performance.

- Newspaper microfilmed 2 sheets per frame should be split into two separate image files (and assigned appropriate metadata)

- Images with more than 3 degrees of skew should be deskewed.

- Images should be cropped to the page edge (not to the text block boundaries), retaining the actual edge and up to ¼ inch beyond.

- All operations that change the image dimensions, spatial resolution, or orientation must be made to the TIFF before OCR.

OCR Details

- One OCR text file per page image.

- Each OCR text file name corresponds to the page image it represents

- Text in UTF-8 character set.

- No graphic elements saved with OCR text.

- OCR text ordered column by column

- OCR text file with bounding-box coordinate data at the word level.

- OCR will conform to the ALTO XML schema

Other Derivative Files

PDF

- PDF image with hidden text for each page image

- Each searchable PDF filename corresponds to the page image it represents

- PDF files should incorporate appropriate XMP metadata per Technical Guidelines: Appendix B – File Format Profiles

- Page image will be grayscale downsampled to 150 dpi and encoded using a medium JPEG quality setting

- PDF will not contain any bookmarks, links, named destinations, comments, forms, java script actions, external cross-references, alternate images, embedded thumbnails, annotations, or private data.

JPEG2000

- JPEG2000 images for each page image

- Each JPEG2000 will incorporate appropriate XMP metadata per Technical Guidelines: Appendix B – File Format Profiles

- JPEG2000 will be 6 decomposition levels and 25 quality levels

- JPEG2000 compression will be 8:1

1.3	MINIMUM QUALIFICATIONS

The CONSULTANT must be licensed to do business in the State of Washington.  The CONSULTANT must have five (5) years experience in scanning and production of metadata using XML.

1.4	FUNDING

The AGENCY has budgeted an amount not to exceed $128,000 through June 30, 2010.

Any contract awarded as a result of this procurement is contingent upon the availability of funding.

1.5		PERIOD OF PERFORMANCE

The period of performance of a contract resulting from this RFP is tentatively scheduled to begin on date of execution of the contract which is on or about November 17, 2008, and to end on June 30, 2010. Amendments extending the period of performance, if any, shall be at the sole discretion of the AGENCY.

1.6		DEFINITIONS

Definitions for the purposes of this RFP include:

AGENCY – The Office of the Secretary of State is the agency of the State of Washington that is issuing this RFP.

CONSULTANT – Individual or company submitting a proposal in order to attain a contract with the AGENCY.

CONTRACTOR – Individual or company whose proposal has been accepted by the AGENCY and is awarded a fully executed, written contract.

Proposal – A formal offer submitted in response to this solicitation.

Request for Proposals (RFP) – Formal procurement document in which a service or need is identified but no specific method to achieve it has been chosen.  The purpose of an RFP is to permit the CONSULTANT community to suggest various approaches to meet the need at a given price.

2.	GENERAL INFORMATION FOR CONSULTANTS

2.1	RFP COORDINATOR

The RFP Coordinator is the sole point of contact in the AGENCY for this procurement. All communication between the CONSULTANT and the AGENCY upon receipt of this RFP shall be with the RFP Coordinator, as follows:

| Name | Marlys Rudeen |
| --- | --- |
| Address | PO Box 42460 |
| City, State, Zip Code | Olympia, WA 98504-2460 |
| Phone Number | 360.704.7132 |
| Fax Number | 360.586.7575 |
| E-Mail Address | mrudeen@secstate.wa.gov |

Physical mailing address:  Washington State Library

6880 Capitol Blvd. SE

Tumwater, WA 98501

Any other communication will be considered unofficial and non-binding on the AGENCY.  CONSULTANTS are to rely on written statements issued by the RFP Coordinator.  Communication directed to parties other than the RFP Coordinator may result in disqualification of the CONSULTANT.

2.2		ESTIMATED SCHEDULE OF PROCUREMENT ACTIVITIES

| Issue Request for Proposals | 9/15/08 |
| --- | --- |
| Question and answer period | 9/15/08 – 9/30/08 |
| Place addendum to RFP on AGENCY web site: (if applicable) | 10/1/08 |
| Proposals due | 10/15/08 |
| Evaluate proposals | 10/15/08 – 10/24/08 |
| Announce “Apparent Successful Contractor” and send notification via fax or e-mail to unsuccessful proposers | 10/24/08 |
| Hold debriefing conferences (if requested) | 10/30/08 |
| Negotiate contract | 10/27/08 – 11/15/08 |
| Begin contract work | 11/17/08 |

The AGENCY reserves the right to revise the above schedule.

The RFP will be posted on the AGENCY’s web site http://www.secstate.wa.gov/office/procurements.aspx on or after the issuing date of the RFP. The AGENCY will also post on the same web site any written questions received and responses deemed to be relevant to the solicitation, and any and all addendum changes to the RFP.  It is the responsibility of the CONSULTANT to check the web site for information related to this RFP. The AGENCY will not mail the supplemental information to bidders and will not be responsible for bidder failure to be aware of clarifying information or addendum to the RFP.

2.3		SUBMISSION OF PROPOSALS

CONSULTANT shall submit four (4) copies of proposal. Two copies must have original signatures and two copies can have photocopied signatures.  The proposal, whether mailed or hand delivered, must arrive at the AGENCY no later than 4:30 p.m., local time, on October 15, 2008.

The proposal is to be sent to the RFP Coordinator at the address noted in Section 2.1.  The envelope should be clearly marked to the attention of the RFP Coordinator.

CONSULTANT mailing proposals should allow normal mail delivery time to ensure timely receipt of their proposals by the RFP Coordinator.  CONSULTANTS assume the risk for the method of delivery chosen.  The AGENCY assumes no responsibility for delays caused by any delivery service.  Proposals may not be transmitted using electronic media such as facsimile transmission.

Late proposals will not be accepted and will be automatically disqualified from further consideration. All proposals and any accompanying documentation become the property of the AGENCY and will not be returned.

2.4		PROPRIETARY INFORMATION/PUBLIC DISCLOSURE

Materials submitted in response to this competitive procurement shall become the property of the AGENCY.

All proposals received shall remain confidential until the contract, if any, resulting from this RFP is signed by the AGENCY and the apparent successful CONTRACTOR; thereafter, the proposals shall be deemed public records as defined in RCW 42.17.250 to 42.17.340, “Public Records.”

Any information in the proposal that the CONSULTANT desires to claim as proprietary and exempt from disclosure under the provisions of RCW 42.17.250 to 42.17.340 must be clearly designated.  The page must be identified and the particular exception from disclosure upon which the CONSULTANT is making the claim.  Each page claimed to be exempt from disclosure must be clearly identified by the word “Confidential” printed on the lower right hand corner of the page.

The AGENCY will consider a CONSULTANT’s request for exemption from disclosure; however, the AGENCY will make a decision predicated upon chapter 42.17 RCW and chapter 143-06 of the Washington Administrative Code.  Marking the entire proposal exempt from disclosure will not be honored.  The CONSULTANT must be reasonable in designating information as confidential.  If any information is marked as proprietary in the proposal, such information will not be made available until the affected proposer has been given an opportunity to seek a court injunction against the requested disclosure.

A charge will be made for copying and shipping, as outlined in RCW 42.17.300.  No fee shall be charged for inspection of contract files, but twenty-four (24) hours notice to the RFP Coordinator is required.  All requests for information should be directed to the RFP Coordinator.

2.5		REVISIONS TO THE RFP

In the event it becomes necessary to revise any part of this RFP, addenda will be published on the AGENCY web site, http://www.secstate.wa.gov/office/procurements.aspx, on or about October 1, 2008. For this purpose, any pertinent information and answers to substantive questions by CONSULTANTS from the Question and Answer Period shall be considered an addendum to the RFP and also placed on the web site.

The AGENCY also reserves the right to cancel or to reissue the RFP in whole or in part, prior to execution of a contract.

2.6		MINORITY & WOMEN-OWNED BUSINESS PARTICIPATION

In accordance with the legislative findings and policies set forth in chapter 39.19 RCW, the state of Washington encourages participation in all of its contracts by firms certified by the Office of Minority and Women’s Business Enterprises (OMWBE).  Participation may be either on a direct basis in response to this solicitation or on a subcontractor basis.  However, no preference will be included in the evaluation of proposals, no minimum level of MWBE participation shall be required as a condition for receiving an award, and proposals will not be rejected or considered non-responsive on that basis.  Any affirmative action requirements set forth in federal regulations or statutes included or referenced in the contract documents will apply.

The established annual procurement participation goals for MBE is 8 percent and for WBE,

4 percent, for this type of project.  These goals are voluntary.  Bidders may contact OMWBE at 360/753-9693 to obtain information on certified firms.

2.7	ACCEPTANCE PERIOD

Proposals must provide sixty (60) calendar days for acceptance by AGENCY from the due date for receipt of proposals.

2.8		RESPONSIVENESS

All proposals will be reviewed by the RFP Coordinator to determine compliance with administrative requirements and instructions specified in this RFP.  The CONSULTANT is specifically notified that failure to comply with any part of the RFP may result in rejection of the proposal as non-responsive.

The AGENCY also reserves the right, however, at its sole discretion to waive minor administrative irregularities.

2.9	MOST FAVORABLE TERMS

The AGENCY reserves the right to make an award without further discussion of the proposal submitted.  Therefore, the proposal should be submitted initially on the most favorable terms which the CONSULTANT can propose.  There will be no best and final offer procedure.  The AGENCY does reserve the right to contact a CONSULTANT for clarification of its proposal.

The CONSULTANT should be prepared to accept this RFP for incorporation into a contract resulting from this RFP.  Contract negotiations may incorporate some or all of the CONSULTANT’s proposal.  It is understood that the proposal will become a part of the official procurement file on this matter without obligation to the AGENCY.

2.10	CONTRACT AND GENERAL TERMS & CONDITIONS

The apparent successful contractor will be expected to enter into a contract which is substantially the same as the sample contract and its general terms and conditions attached as Exhibit B.  In no event is a CONSULTANT to submit its own standard contract terms and conditions in response to this solicitation.  The CONTRACTOR may submit exceptions as allowed in the Certifications and Assurances section, Exhibit A to this solicitation.  The AGENCY will review requested exceptions and accept or reject the same at its sole discretion.

2.11	COSTS TO PROPOSE

The AGENCY will not be liable for any costs incurred by the CONSULTANT in preparation of a proposal submitted in response to this RFP, in conduct of a presentation, or any other activities related to responding to this RFP

2.12	NO OBLIGATION TO CONTRACT

This RFP does not obligate the State of Washington or the AGENCY to contract for services specified herein.

2.13	REJECTION OF PROPOSALS

The AGENCY reserves the right at its sole discretion to reject any and all proposals received without penalty and not to issue a contract as a result of this RFP.

2.14	COMMITMENT OF FUNDS

The Assistant Secretary of State or his delegates are the only individuals who may legally commit the AGENCY to the expenditures of funds for a contract resulting from this RFP.  No cost chargeable to the proposed contract may be incurred before receipt of a fully executed contract.

2.15       ELECTRONIC PAYMENT

The State of Washington prefers to utilize electronic payment in its transactions.  The successful contractor will be provided a form to complete with the contract to authorize such payment method.

2.16      INSURANCE COVERAGE

Should a contract be awarded pursuant to this RFP, the CONTRACTOR will be required to provide insurance coverage as described in Exhibit B, Sample Purchased Service Contract with General Terms and Conditions.

2.17      WORKER’S COMPENSATION COVERAGE

The CONTRACTOR will at all times comply with all applicable workers’ compensation, occupational disease, and occupational health and safety laws, statutes, and regulations to the full extent applicable.  The State will not be held responsive in any way for claims filed by the CONTRACTOR or their employees for services performed under the terms of this contract.

3.	PROPOSAL CONTENTS

Proposals must be submitted on eight and one-half by eleven (8 1/2 x 11) inch paper with tabs separating the major sections of the proposal. The major sections of the proposal are to be submitted in the order noted below:

- Letter of Submittal, including signed Certifications and Assurances (Exhibit A).

- Management Proposal.

- Cost Proposal.

- References.

Proposals must provide information in the same order as presented in this document with the same headings.  This will not only be helpful to the evaluators of the proposal, but should assist the CONSULTANT in preparing a thorough response.

Items in this section marked “mandatory” must be included as part of the proposal for the proposal to be considered responsive; however, these items are not scored.  Items marked “scored” are those that are awarded points as part of the evaluation conducted by the evaluation team.

3.1		LETTER OF SUBMITTAL (MANDATORY)

The Letter of Submittal and the attached Certifications and Assurances form (Exhibit A) must be signed and dated by a person authorized to legally bind the CONSULTANT to a contractual relationship, e.g., the President or Executive Director if a corporation, the managing partner if a partnership, or the proprietor if a sole proprietorship.  Along with introductory remarks, the Letter of Submittal is to include by attachment the following information about the CONSULTANT and any proposed subcontractors:

- Name, address, principal place of business, telephone number, and fax number/e-mail address of legal entity or individual with whom contract would be written.

- Name, address, and telephone number of each principal officer (President, Vice President, Treasurer, Chairperson of the Board of Directors, etc.).

- Legal status of the CONSULTANT (sole proprietorship, partnership, corporation, etc.) and the year the entity was organized to do business as the entity now substantially exists.

- Federal Employer Tax Identification number or Social Security number and the Washington Uniform Business Identification (UBI) number issued by the State of Washington Department of Revenue.

- Location of the facility from which the CONSULTANT would operate.

- Identify any State employees or former State employees employed or on the firm’s governing board as of the date of the proposal.  Include their position and responsibilities within the CONSULTANT’s organization.  If following a review of this information, it is determined by the AGENCY that a conflict of interest exists, the CONSULTANT may be disqualified from further consideration for the award of a contract.

3.2		MANAGEMENT PROPOSAL

A.	Project Management (SCORED)

- Project Team Structure/Internal Controls - Provide a description of the proposed project team structure and internal controls to be used during the course of the project, including any subcontractors. Provide an organizational chart of your firm indicating lines of authority for personnel involved in performance of this potential contract and relationships of this staff to other programs or functions of the firm.  This chart must also show lines of authority to the next senior level of management.  Include who within the firm will have prime responsibility and final authority for the work.

- Staff Qualifications/Experience – Identify staff, including subcontractors, who will be assigned to the potential contract, indicating the responsibilities and qualifications of such personnel, and include the amount of time each will be assigned to the project.  Provide resumes' for the named staff, which include information on the individual’s particular skills related to this project, education, experience, significant accomplishments and any other pertinent information. The CONSULTANT must commit that staff identified in its proposal will actually perform the assigned work.  Any staff substitution must have the prior approval of the AGENCY.

B.	Experience of the Consultant (SCORED)

1.  Indicate the experience the CONSULTANT and any subcontractors have in the following areas: scanning from microfilm, optical character recognition (OCR), use of METS/ALTO standards, creation of metadata, and use of XML templates.

2.   Indicate other relevant experience that indicates the qualifications of the CONSULTANT, and any subcontractors, for the performance of the potential contract.

- Include a list of contracts the CONSULTANT has had during the last five years that relate to the CONSULTANT’s ability to perform the services needed under this RFP.  List contract reference numbers, contract period of performance, contact persons, telephone numbers, and fax numbers/e-mail addresses.

C.	Related Information (MANDATORY)

- If the CONSULTANT or any subcontractor contracted with the State of Washington during the past 24 months, indicate the name of the agency, the contract number and project description and/or other information available to identify the contract.

- If the CONSULTANT’s staff or subcontractor’s staff was an employee of the State of Washington during the past 24 months, or is currently a Washington state employee, identify the individual by name, the AGENCY previously or currently employed by, job title or position held and separation date.

- If the CONSULTANT has had a contract terminated for default in the last five years, describe such incident. Termination for default is defined as notice to stop performance due to the CONSULTANT’s non-performance or poor performance and the issue of performance was either (a) not litigated due to inaction on the part of the CONSULTANT, or (b) litigated and such litigation determined that the CONSULTANT was in default.

- Submit full details of the terms for default including the other party's name, address, and phone number.  Present the CONSULTANT’s position on the matter.  The AGENCY will evaluate the facts and may, at its sole discretion, reject the proposal on the grounds of the past experience.  If no such termination for default has been experienced by the CONSULTANT in the past five years, so indicate.

E.	OMWBE Certification (Optional)

Include proof of certification issued by the Washington State Office of Minority and Women-Owned Business if certified minority-owned firm and/or women-owned firm(s) will be participating on this project.

3.3		COST PROPOSAL

The maximum fee for this contract must be $128,000 or less to be considered responsive to this RFP.

The evaluation process is designed to award this procurement not necessarily to the CONSULTANT of least cost, but rather to the Consultant whose proposal best meets the requirements of this RFP.  However, CONSULTANTS are encouraged to submit proposals which are consistent with State government efforts to conserve state resources.

A.	Identification of Costs (SCORED)

Identify all costs including expenses to be charged for performing the services necessary to accomplish the objectives of the contract.

Provide a price breakdown for the services indicated below.  Include the charge per image, broken down by the following services:

- Scanning, deskewing, and cropping.

- OCR.

- Derivative files

- Integration of Library-supplied metadata

- METS encoded metadata files.

- Shipping and handling.

- Any other costs for the described products.

The CONSULTANT is to submit a fully detailed budget including staff costs and any expenses necessary to accomplish the tasks and to produce the deliverables under the contract.  CONSULTANTS are required to collect and pay Washington state sales tax, if applicable.

Costs for subcontractors are to be broken out separately.  Please note if any subcontractors are certified by the Office of Minority and Women’s Business Enterprises.

B.	Computation

The score for the cost proposal will be computed by dividing the lowest cost bid received by the CONSULTANT’s total cost.  Then the resultant number will be multiplied by the maximum possible points for the cost section.

3.4	References (SCORED)

List names, addresses, telephone numbers, and fax numbers/e-mail addresses of three business references for which work has been accomplished and briefly describe the type of service provided.  The CONSULTANT must grant permission to the AGENCY to contact the references.  Do not include current AGENCY staff as references.  References will be contacted for the top-scoring proposal(s) only.

4.	EVALUATION AND CONTRACT AWARD

4.1		EVALUATION PROCEDURE

Responsive proposals will be evaluated strictly in accordance with the requirements stated in this solicitation and any addenda issued.  The evaluation of proposals shall be accomplished by an evaluation team, to be designated by the AGENCY, which will determine the ranking of the proposals.

AGENCY, at its sole discretion, may elect to select the top-scoring firms as finalists for an oral presentation.

4.2		EVALUATION WEIGHTING AND SCORING

The following weighting and points will be assigned to the proposal for evaluation purposes:

| Management Proposal - (25 points) Demonstrated quantity and quality of successful relevant experience. - Breadth of experience in reformatting technologies. - Experience in newspaper preservation and reformatting. - Experience in large scanning projects. - (25 points) Previous experience with NDNP projects. - Number of projects. - Level of participation in projects. - Level of satisfaction reported by project managers. - (15 points) Demonstrated level of organizational ability. - Size of company, length of time in reformatting industry. - Experience in management and line staff assigned to projects. - Quality of strategic partnerships. | 65 points |
| --- | --- |
| Cost Proposal - Price breakdown for scanning, processing - OCR - Creation of derivative files - Integration and encoding of metadata - Shipping and other costs | 10 points |
| Sub-Total for Written Proposal | 75 points |
| References [top-scoring proposer(s) only] | 25 points |
| GRAND TOTAL | 100 POINTS |

References will be contacted for the top-scoring CONSULTANT (s) only, based on the written proposal. References will then be scored and included in the Grand Total.

4.4		NOTIFICATION TO PROPOSERS

Firms whose proposals have not been selected for further negotiation or award will be notified via FAX or by e-mail.

4.5		DEBRIEFING OF UNSUCCESSFUL PROPOSERS

Upon request, a debriefing conference will be scheduled with unsuccessful CONSULTANTS.  The request for a debriefing conference must be received by the RFP Coordinator within three (3) business days after the Notification of Unsuccessful proposal letter is faxed/e-mailed to the CONSULTANT.  The debriefing must be held within three (3) business days of the request.

Discussion will be limited to a critique of the requesting CONSULTANT’s proposal.   Comparisons between proposals or evaluations of the other proposals will not be allowed.  Debriefing conferences may be conducted in person or on the telephone and will be scheduled for a maximum of one hour.

4.6		PROTEST PROCEDURE

This procedure is available to CONSULTANTS who submitted a response to this solicitation document and who have participated in a debriefing conference.  Upon completing the debriefing conference, the CONSULTANT is allowed three (3) business days to file a protest of the acquisition with the RFP Coordinator.  Protests may be submitted by facsimile, but should be followed by the original document.

CONSULTANT protesting this procurement shall follow the procedures described below.  Protests that do not follow these procedures shall not be considered.  This protest procedure constitutes the sole administrative remedy available to CONSULTANTS under this procurement.

All protests must be in writing and signed by the protesting party or an authorized Agent.  The protest must state the grounds for the protest with specific facts and complete statements of the action(s) being protested.  A description of the relief or corrective action being requested should also be included.  All protests shall be addressed to the RFP Coordinator.

Only protests stipulating an issue of fact concerning the following subjects shall be considered:

- A matter of bias, discrimination or conflict of interest on the part of the evaluator.

- Errors in computing the score.

- Non-compliance with procedures described in the procurement document or AGENCY policy.

Protests not based on procedural matters will not be considered.  Protests will be rejected as without merit if they address issues such as:  1) an evaluator’s professional judgment on the quality of a proposal, or 2) AGENCY’S assessment of its own and/or other agencies needs or requirements.

Upon receipt of a protest, a protest review will be held by the AGENCY.  The Secretary of State or an employee delegated by the Secretary of State who was not involved in the procurement will consider the record and all available facts and issue a decision within five business days of receipt of the protest.  If additional time is required, the protesting party will be notified of the delay.

In the event a protest may affect the interest of another CONSULTANT which submitted a proposal, such CONSULTANT will be given an opportunity to submit its views and any relevant information on the protest to the RFP Coordinator.

The final determination of the protest shall:

- Find the protest lacking in merit and uphold the AGENCY’s action; or

- Find only technical or harmless errors in the AGENCY’s acquisition process and determine the AGENCY to be in substantial compliance and reject the protest; or

- Find merit in the protest and provide the AGENCY options which may include:

–Correct the errors and re-evaluate all proposals, and/or

–Reissue the solicitation document and begin a new process, or

–Make other findings and determine other courses of action as appropriate.

If the AGENCY determines that the protest is without merit, the AGENCY will enter into a contract with the apparently successful contractor.  If the protest is determined to have merit, one of the alternatives noted in the preceding paragraph will be taken.

5.	RFP EXHIBITS

Exhibit A	Certifications and Assurances

Exhibit B    Sample Purchased Service Contract including General Terms and Conditions

Exhibit C   Certificate of Disbarment and Suspension

Exhibit D   The National Digital Newspaper Program (NDNP) Technical Guidelines 2008-2010

EXHIBIT A

CERTIFICATIONS AND ASSURANCES

I/we make the following certifications and assurances as a required element of the proposal to which it is attached, understanding that the truthfulness of the facts affirmed here and the continuing compliance with these requirements are conditions precedent to the award or continuation of the related contract(s):

- I/we declare that all answers and statements made in the proposal are true and correct.

- The prices and/or cost data have been determined independently, without consultation, communication, or agreement with others for the purpose of restricting competition.  However, I/we may freely join with other persons or organizations for the purpose of presenting a single proposal.

3.	The attached proposal is a firm offer for a period of 60 days following receipt, and it may be accepted by the AGENCY without further negotiation (except where obviously required by lack of certainty in key terms) at any time within the 60-day period.

4.	In preparing this proposal, I/we have not been assisted by any current or former employee of the state of Washington whose duties relate (or did relate) to this proposal or prospective contract, and who was assisting in other than his or her official, public capacity.  (Any exceptions to these assurances are described in full detail on a separate page and attached to this document.)

5.	I/we understand that the AGENCY will not reimburse me/us for any costs incurred in the preparation of this proposal.  All proposals become the property of the AGENCY, and I/we claim no proprietary right to the ideas, writings, items, or samples, unless so stated in this proposal.

6.	Unless otherwise required by law, the prices and/or cost data which have been submitted have not been knowingly disclosed by the Proposer and will not knowingly be disclosed by him/her prior to opening, directly or indirectly to any other Proposer or to any competitor.

7.	I/we agree that submission of the attached proposal constitutes acceptance of the solicitation contents and the attached sample contract and general terms and conditions.  If there are any exceptions to these terms, I/we have described those exceptions in detail on a page attached to this document.

8.	No attempt has been made or will be made by the Proposer to induce any other person or firm to submit or not to submit a proposal for the purpose of restricting competition.

___________________________________________

Signature of Proposer

___________________________________________

Title				     	Date